## Sheet2
TASK | DURATION | COMMENTS
Buying | Anytime from 3 month ahead. | You can buy the turkey at any time and still make your deadline. To get the best price, you might buy it 3 months in advance.
Thawing | 36 hours | you need to know the exact number of pounds in order to determine how long to thaw the turkey ( three hours per pound). And once thawed, your turkey needs to go directly to the cooking stage. Let's assume you are preparing a twelve-pound turkey. You can estimate that it will take thirty-six hours to thaw. This will be a critical path item
Determine the method of cooking. | Up to you | You can determine this long before.
Caculate the cooking time | Up to calculation | You can do this as soon as you know how much the turkey weighs
Preheat oven | 1 hour | You can start preheating while the turkey thaws
Cooking | 26 hours | Without the proper cooking time, you'll find yourself with a buch of sick guests We will estimate thirteen minutes cooking time per pound for our twelve-pound bird: 13*12 pounds = 2.6 hours This will be a critical path item.
Resting | 0.5 hours | You can estimate 30-minute rest period after the turkey has finished cooking. This will be critical path item
Carving | 0.2 hours | You can put the turkey on the table right at 4pm and carve each piece as you serve it to your guests This is a critical path item
Arrange tables and chairs | 0.5 hours | We can perform the next three table setting activities while the turkey is cooking.
Position table cloth and centerpiece | 0.25 hours
Set china and silverware | 0.25 hours