## Sheet1
| STATUS | %DONE | DLIVERABLES / COMPONENTS / ACTIVITIES | WORK HOURS | DURATION | START DATE | END DATE
2 |  |  | RELOCATION | 248 | 38 days | 1st Oct | 7th Nov
2.1 |  |  | Relocation package | 116 | 33 days | 1st Oct | 2nd Nov
2.1.1 |  |  | Obtain HR Input | 24 | 3 days | 1st Oct | 3rd Nov
2.1.2 |  |  | Establish Moving Allowance | 6 | 2 days | 4th Oct | 5th Oct
2.1.3 |  |  | Determine Incentives | 6 | 2 days | 4th Oct | 5th Oct
2.1.4 |  |  | Draft Documentation | 16 | 4 days | 6th Oct | 9th Oct
2.1.5 |  |  | Gain Legal Approval | 8 | 3 days | 10th Oct | 12th Oct
2.1.6 |  |  | Source Contracts | 56 | 14 | 20th Oct | 2nd Nov
2.2 |  |  | Budget | 32 | 25 days | 13th Oct | 7th Nov
2.2.1 |  |  | Perform Cost Study | 16 | 5 days | 13th Oct | 17th Oct
2.2.2 |  |  | Obtain Board Approval | 8 | 5 days | 18th Oct | 20th Oct
2.2.3 |  |  | Determine # of Employee Relocating | 2 | 1 day | 6th Nov | 6th Nov
2.2.4 |  |  | Checks Disbursement | 6 | 1 day | 7th Nov | 7th Nov
2.3 |  |  | Location Visit | 36 | 10 days | 10th Oct | 19th Oct
2.3.1 |  |  | Establish Agenda | 16 | 3 days | 10th Oct | 12th Oct
2.3.2 |  |  | Contact City Hosts | 8 | 5 days | 13th Oct | 17th Oct
2.3.3 |  |  | Determin Airfare | 4 | 1 day | 17th Oct | 17th Oct
2.3.4 |  |  | Secure Hotel | 8 | 3 days | 17th Oct | 19th Oct
2.4 |  |  | City Information | 34 | 6 days | 13th Oct | 18th Oct