## Sheet1
[8 empty] | 2014-12-31 00:42 | 2015-01-01 | 2015-01-01 12:00
| DELIVERABLES / COMPONENTS / ACTIVITIES | PREDECESSOR | WORK HOURS | DURATION | START DATE | END DATE | WHO
1 | TURKEY PREPARATION |  | 40.3 hours | 40.3 hours |  |  | Mom
1.1 | Thaw Turkey |  | 36 hours | 36 hours | Dec.31 | Jan.1 | Mom
1.2 | Pre-heat Oven |  | 1 hour | 1 hour | 11:42 | 12:42 | Mom
1.3 | Cook Bird | 1.1, 1.2 | 2.6 hour | 2.6 hour | 12:42 | 15:18 | Mom
1.4 | Rest Turkey | 1.3 | 0.5 hour | 0.5 hour | 15:18 | 15:48 | Mom
1.5 | Present Turkey, Carve and Serve | 1.4, 2.3 | 0.2 hour | 0.2 hour | 15:48 | 16:00 | Mom
2 | TABLE SETTING | [5 empty] | Teen
2.1 | Arrange Table and Chairs |  | 0.5 hour | 0.5 hour | 14:30 | 15:00 | Teen
2.2 | Position Tablecloth and Centerpiece | 2.1 | 0.25 hour | 0.25 hour | 15:00 | 15:15 | Teen
2.3 | Set China and Silverware | 2.2 | 0.25 hour | 0.25 hour | 15:30 | 15:45 | Teen